## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Sheet1
| Table 1 | Sheet1

## Sheet1
Section | Environment | Task | Current | New | Cost | Days | Resource | Testing | Signoff | Importance | Comment | Possible start date
EQ 1 | Basic edits, renames etc | Edit title details: Change description on Local Media works e-mail from 'Email' to 'Advertising Email'; Edit title details: remove website URL from group/company page as information is also in the EQ Edit circulation details: Rename 'Circulation' field to 'Total Circulation'. | Email website URL Circulation | Advertising Email removed Total Circulation |  | 0.5 |  |  |  | Low
EQ 2 | Edit circulation details (3) | Audit Period and Audit code information to be included in this page (currently to be found in Edit title details - remove from here, and transfer. | On Edit title details section | To appear on edit circulation screen where input by sector is carried out |  | 1 |  |  |  | High
EQ 3 | Edit circulation details (4 & 5) | As well as having the input box for total circulation, there should be three new input boxes, paid circulation, free door to door circulation and free pick up circulation. These three new boxes should add to the total circulation. If they don't an error message should flag and the input rejected. Remove auto allocate from top area. | New feature | Appears on edit circulation screen |  | 2 |  |  |  | High
EQ 4 | Edit circulation details (6) | Update autoallocate option with a new autoallocate formulae to be added to the edit circulation details page. The formula should allow for the proportional allocation of copies rounded up or down for each of the three route to market segments so that its total always matches the audited figures for Total Circulation. Any unallocated copies due to rounding to be added to largest figure. | Update feature to include new data in EQ3 | Appears on edit circulation screen |  | 2 |  |  |  | High
EQ 5 | Edit circulation details (7) | When adding new postcode sectors from the add function, output needs to show correct location name, households and population. |  |  |  | 1 |  |  |  | Medium
EQ 6 | Edit circulation details (8) | The export function currently exports the following fields Postcode sector, Paid circ, free door to door and free pick up but does not export the location definition, the household counts and total circulation figure which would make the output figure understandable. |  |  |  | 1.5 | 8 |  |  | Medium
EQ BUG! | Edit circulation details (9) | User time out when submit button entered. We must understand how this occurs primarily on substantial submissions that take longer to complete |  |  | Investigate | ? |  |  |  | Medium | POSS BUG Can we test or get examples?
EQ BUG2 | Edit circulation details (10) | Error message for new titles on the database. When a new title is added to EQ database, it doesn't allow you to input new circ figures by postcode as it generates an error when you go to submit. |  |  | Investigate | ? |  |  |  | Medium | POSS BUG Can we test or get examples?
EQ BUG3 | Newspaper section (1) | The date of amendment does not always update on the Newspaper section page in all fields (4) in a consistent manner |  |  | To investigate. Should already have been fixed? | ? |  |  |  | High | POSS BUG
JO TI | JO-T1 (Template 1) Results template - web page display | All results pages are to use the basic template form in this page, which includes a basic grid system, using coloured headings for different sections. Header and Footer to be the same in all cases. Header of page to include: Jicreg Online logo (as standard header used in all non-results pages) Name and date of report (name may be user defined or ‘Standard report’) Row of four options: Back, Print, Export csv and Save Report (inc. naming dialogue) Main body of page to contain: 1. Newsbrand of geographical summary section followed by 2. Detailed tables as per references below and illustrations Footer of page to include: 1. Link to a standard glossary of terms 2. Source date and copyright info 3. Then as per current footer as used in non-results pages | [7 empty] | High
JO TI | JO-T1 (Template 1) Results template - .csv export | The existing format is suitable, with the following amendments 1. All excel files exported must have the file extension .csv suffixed to filename 2. All excel files exported should have unique name – suggest include date/time 3. All excel files must contain source date beneath data, in column A | [7 empty] | High
JO 1 | JO - reports section (1) | Replace current text on the page, with new text supplied and re-order report options as per diagram |  |  |  | 0.5 | 0.5 |  |  | High
JO 2 | JO - reports section (2) | Build new page comprising a glossary of terms (list to be provided by KD) Page to use standard header/footer |  |  |  | ? |  |  |  | High
JO 3 | JO - reports section - standard reports (2) | Replace current single form entry with two options: either select Newsbrand (results to JO-9) or select geographical area (Results to JO-10) | area search | standard report geographic area OR Newsbrand | To Investigate | 3 |  |  |  | Medium
JO 4 | JO - reports section - standard reports (3) | Newsbrand standard report output. Report to use template JT-1 layout. Results to be displayed as per illustration JO-x; unavailable data to show N/A |  |  | To Investigate | 6 |  |  |  | High
JO 5 | JO - reports section - standard reports (4) | Any geographic standard report output. Report to use template JT-1 layout. Results to be displayed as per illustration JO-x | figures displayed in coloured segments | figures in a grid system. Area profile in 000s and % at the top. News brands to show all adult figures and %Air for Total Audience, Total online, total mobile, total PC and total print. Glossary of terms to appear on every report. | To Investigate | 4 |  |  |  | High
JO 6 | JO - drivetime section (1) | Form entry box to accept either postcode sector (as current) or full postcode and to generate appropriate results in each case. | postcode sector | postcode sector or full postcode. Invalid entry to produce alert | Needs new DB | 4 |  |  |  | Medium
JO 7 | JO - drivetime section (2) | Drivetimes to be calculated using 'peak' and 'off-peak' average speeds. User to select which is required by checking 'Peak' or 'Off peak' option when completing form. | no option at present | Peak or off-peak av speed to be used when calculating results | To Investigate | 1 |  |  |  | Medium
JO 8 | JO - drivetime section (3) | Many users will save the list and then use it in either audience analysis or Create your own reports. Check this option is clear | Currently the system then generates a report based on the drive time area and a map | The saved catchment area can be run in audience analysis or create your own report. | To Investigate | 6 | 24 |  |  | Medium
| JO - drive time section | Drive time to start at the postcode | Currently starts at middle of the sector | To start at postcode | Same as JO 6? | ?
JO 9 | JO - Create your own report (1-9) | (1) Save facility for created reports - to have the ability to save any selection of geographies, enabling user to save lengthy lists. | No option to save geographies. | save facility for any selection of geographies | Need a save list option at http://jicregonline.co.uk/create-location/1 | 4 |  |  |  | Medium
JO 10 | Create your own report - Entry page | There should be three identifiable options available to users. 1. Build new list 2. Search for saved list (from this or drivetime), allow multiple selection 3. Search for previously saved report | Option 3 isn't there at all Option 1 isn't identified | Add option to select multiple lists; also add option to select a previous report with the same formatting. |  | 3 |  |  |  | High
JO 11 | Create your own report - Add locations page | 1. Include ability to name and save the completed list. If Next Step is selected and list has not been saved, prompt user 2. Currently, user cannot mix and match geographies and postcode sectors in this section, yet they can in other areas | not currently there | new free text save dialogue |  | 2 |  |  |  | Medium
JO 12 | Create your own report - Results | Uses Template JT-01 ofr output Results include: Demographic profile of the area Location report |  | Run into new standard template, with print, export and save options |  | 4
JO 13 | Create your own report | (7a &7 b) Output report - currently when you select your variables in Add Fields. The 'Area and Title' should be one list. This allows the user to then 'order fields' as they'd like them to appear in the report. | Currently chose order of total household, AIR %, RPC, Circulation etc and then order of demographics separately | Variables need to be listed altogether so you can order them as you want them to appear on report, also need to incorporate new total audience, online, mobile, pc and print audiences. Once change is made then user will be able change order as required. | NEEDS MORE INPUT HELP | 2 | 15 |  |  | Medium
JO B 1 | Create your own report | (5) Reporting hang - occasionally the report output hangs although the pulsing circle at bottom of page is active, the report does not load. |  | Maybe a user issue? | POSS BUG | ?
JO B 2 | Create your own report | (6) Reporting failure - when select standard geographies, system fails to return demographic data when selecting a saved template. No print data is returned only web data that hasn't been specified. |  | Maybe a user issue? | POSS BUG | ?
JO B 3 | Create your own report | To use .csv template JT-02 (8) CSV output - Some columns are out of sync when exported. Titles with multiple publication days (dailies) the days are output individually so the columns are out of sync. | Misalignment when exported to csv | All data should align against correct heading. | BUG | ? |  |  |  | High
| Create your own report | (9) Additional variable options to be included within output report. | Not currently there awaiting outputs from the models. | Once models are finished we can spec this. |  | TBC |  |  |  | High
| JO - Audience analysis (1) | jicregonline.co.uk/audience-analysis/2 Add option to filter by publisher by adding a drop down list of publishers | Not currently available | New drop down menu of publishers, with default value of 'All', to be placed above Newspapers and Websites heading |  | 3 |  |  |  | High
| JO - Audience analysis (1) | Comprehensive postcode sector dataset. Currently, only postcode sectors where there is any coverage of a title is included in the search facility. All postcodes need to be included. | No visible in the system. | Comprehensive list of postcode sectors to be included. Need to see if sectors with no distribution show up when run against a location. | RSMB to look into this | 4 |  |  |  | High
| JO - Audience Analysis - Add Geography (2) | Save List function - allow users the ability to name and save lists when created. Save in My Account | report saved as date/time stamp | Name report and save under My Account |  | 4 | 11 |  |  | High
| JO - Audience Analysis (3) | System returns you to home screen - intermittent fault occurs when looking at large geographies. Occasionally throws you out and returns you to home screen. |  |  | POSS BUG | ?
| JO - Audience Analysis (4a - 4f) | Defining report - reporting palette/digital audience frequency palette/define report. All these reporting options need to be looked at to define demographics/audience data/data frequency and reporting options to give users choice of reporting options and create bespoke reports. | Not there at present as awaiting outputs of the new models | New reporting options and interlaced demographic options. | Keith to advise, this will be subject to outputs from the models and if in and out of area for online is possible. | TBC |  |  |  | High
| JO Audience Analysis (5a - 5c) | Change of emphasis required on print data to make it more relevant. Reporting output for All Adults do not require same headings as reports that include demographic audiences. | See JO3 as same issue of missing data occurs. Duplication of column data when adults is chosen as an audience. Audience data for websites when exported as a csv generates random numbers | Output of reports need to be amended. (see spec for details) | To Investigate | ? |  |  |  | Medium
| Export planning file at www.jicregonline.co.uk/audience-analysis/4 | Create an option for e-telmar users to either 'save locally' or 'link to e-telmar' | Only possible to save locally and then import to Telmar from local drive. | To provide Telmar with a URL and ftp site. This will establish that they are registered Telmar licenced users. |  | TBC
| JO - Mapping Section (1 -2) | Catchment boundary area should be shown as contiguous area without each postcode sector boundary (as it currently does). New function to be added to manipulate catchment. Change colour/make transparent/border round edge of catchment. Layering of newsbrands over catchment with an adaptive legend to reflect changes. Colour palette and editor to tailor your catchment. | Basic catchment boundary showing all postcode boundaries within catchment | New fully adaptive boundaries and legend with colour palette and editor. | as discussed catchment area can’t be one area as we only have postcode sectors to draw on in the DB. Colour changing fine | ? |  |  |  | High
| JO - Mapping Section (3) | Catchment shading facility - patterns to be introduced for greater clarity on maps along with fully adaptive legend. | Just plain colour at the moment either automatically selected or chosen by user. | pattern tiles to be added to create greater clarity with the legend on map fully adaptive | as discussed could cause issues and overlaps. Won’t make the situation better. Will slow down system. | ? |  |  |  | High
| jo - Mapping Section (4) | Map information toggle - useful info fields: zoom facility from postcode district through to postcode data. Different road types (using different colours). Railway lines and stations. | Not possible at the moment. | Info to be added like roads, railway lines, stations, and ability to zoom from district to postcode data. | we’d need all data for all elements you wish to display. Best bet is we arrange a call with your selected data partner to discuss options. | TBC |  |  |  | High | Infologic have asked following: Given the system is based on Google Maps, I am assuming you would require the map data in KML format or something similar? We can certainly produce that and provide the Postcode boundaries at Area, District and Sector level as required. With regard to the roads, stations, areas of interest and so on, we have a number of options for these including Ordnance Survey or Collins Bartholomew data and, again, should be able to provide these in a format you can use. Will these overlay the Google Maps in your system and just act as a visual reference for your customers or will they have some other purpose? Obviously Google has a lot of this information already built into their maps so it would be good to know the purpose of adding this extra information to your system. To be able to determine which option is best for you we would need to know exactly which layers of information you need such as whether you need all main roads or detailed streets and which points of interest and so on. Do you have a list of features you need to source?
| JO - Mapping Section (5) | Adding point sets to map - for example running drive time of dover and having Dover Castle, pinpointed on map. The option to name and choose colour for your pinpoint. | Not possible at the moment. | Adding pinpoints/places of interest on map with colour options. |  | 4 |  |  |  | Medium
| JO - Mapping Section (6) | Newsbrand audience density maps - ability to visualise audience density on map by postcode sector, very useful facility when EQ data needs to be uploaded to ensure lakes/islands (holes in map) are minimised. | Not possible at the moment. | audience density facility by postcode sector. |  | 5 |  |  |  | Low
JO 26 | JO - My Account (1) | Changes above mean that lists will now be named by the user when saved | Lists saved in date order | Introduce text search facility or list them alphabetically. | 1200 | 2 |  |  |  | High
JO 27 | JO - My Account (2) | Ability to select multiple lists to delete at one time. 'Delete' check box against each list entry | Each list currently has to be deleted individually. | function to delete lists more efficiently and ability to select multiple lists to delete. |  | 3 |  |  |  | High
JO 28 | JO - My Account (3) | Ability to create folders in my lists to save catchments. |  | Folder structure to store catchments |  | 4 |  |  |  | Low
JO 29 | JO - My Account (4) | When exporting catchments from my account, the system adds a space if the sector has a single numeric prefix. For use within other applications you have to remove these spaces and resave in excel. This needs to be amended. | Export of catchments inputs a space between a single numeric prefix. E.g., N3 1 becomes N 3 1 | Remove space if a single numeric prefix is listed. | RSMB | 0.5 | 18.5
JO 30 | JO - Information Archive (1) | Archive datasets - currently only historic print figures are listed. Need to list print and web figures and list in excel rather than pdf | Print only historical data | Print and online figures to be listed in excel format. | Leave this - Keith to check. KD this is something we can generate ourselves via RSMB and with CMS upload ourselves. | TBC |  |  |  | Low
JO 31 | JO - Information Archive (2) | Dataset output headings - have consistent datasets with logical headings. |  | Amend report output. Logical headings and more data listed on outputs. | Leave this - Keith to check. See above, JICREG can edit and upload through CMS. | TBC |  |  |  | Low
MGMT 1 | JICREG Online administration | To be able to download list of registered users | Static, users can be seen but not able to extract details. | To export all users and their contact details as a csv file |  | 3 | 3 |  |  | High
MGMT2 | JICREG Online administration | Ability to track usage of JICREG Online | Google analytics | To monitor number of reports run, page requests and number of users by specified dates. Also to identify which part of the system is used i.e. standard reports, audience analysis, drive times, mapping or create your own report. To allow analysis by individual or company. | google analytics integration only? | TBC |  |  |  | High
MGMT3 | JICREG User administration | Provide a clear indication in the database of user profile/privileges/paid access available | none | 1) Full JO Access 2) Full JO Access + Mapping 3) Full JO Access + Nationals 4) Full JO Access + Mapping + Nationals 5) Each module within JO to be switched on/off ie. Standard reports, audience analysis, drive time, create report and mapping 6) TELMAR access 7) Administrator 8) Deleted user 9) Guest user | do you mean adding these user types to the DB and changing user access levels based on this? Can they be multiples? | TBC |  |  |  | High
MGMT3 | JICREG Online administration | Password management | Passwords do not expire and manually controlled | a) All user passwords to require updating every six months b) Users to get a reminder 14 days before expiry or at first log in after that time c) The new password must not be the same as the previous three passwords (so would cover two years) d) Realistic password rules: suggest 8 chars min, must include u/c char, l/char, numerals. |  | 3 | 3 |  |  | High
CMS 1 | Content management system | For JICREG to be able to edit text on www.jicreg.co.uk or JICREG Online | Not available | For JICREG admin to be able to update text on both websites as and when needed. | Needs more thorough spec to work out what text and how you wish to update. | TBC |  |  |  | Medium
LMW1 | localmediauk.org | Search facility for Newsbrand or pre-defined geography. | Holding page | For Newsbrand, individual title postal address, email address and phone number. The same for the publisher the title belongs to. The name of the sales house representing the title. Underneath the contact details, a table to include following details from the database: Total circulation, type of newspaper (i.e. pad/free), frequency, number of issues per year, publication days, audit period, audit code, effective date (i.e. when the data was updated), page rate, column centimetre, column length, format (i.e. tabloid/broadsheet), number of columns. Finally text to say, for audience data please visit www.jicreg.co.uk | Needs more discussion | TBC |  |  |  | High
83